## Project Gantt Chart
10-WEEK PROJECT IMPLEMENTATION GANTT CHART
Comprehensive Project Schedule & Milestone Tracker (Weeks 1 to 10)
WBS | Task Description | Start Week | Duration | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10
Phase 1: Setup & Architecture
1.1 | Requirements gathering, proposal, setup, GitHub, initial design | Week 1 | 1 Wk
1.2 | Database schema, API design, wireframes | Week 2 | 1 Wk
1.3 | Start frontend & backend development | Week 2 | 1 Wk
Phase 2: Core Feature Implementation
2.1 | Authentication & user profile modules | Week 3 | 1 Wk
2.2 | Database integration & persistence | Week 3 | 1 Wk
2.3 | Workout generation, diet planning & tracking modules | Week 4 | 1 Wk
Phase 3: Prototype & Advanced Features
3.1 | Finish MVP & submit Prototype | Week 5 | 1 Wk
3.2 | Dashboard, graphs & image upload features | Week 6 | 1 Wk
3.3 | Complete remaining modules & full integration | Week 7 | 1 Wk
Phase 4: QA, Deployment & Submission
4.1 | Testing, bug fixing & UI polish | Week 8 | 1 Wk
4.2 | Final testing & performance optimization | Week 9 | 1 Wk
4.3 | System deployment | Week 9 | 1 Wk
4.4 | Documentation & presentation prep | Week 8 | 3 Wks
4.5 | Final Submission | Week 10 | 1 Wk
Legend / Phase Key:
Phase 1: Setup & Architecture
Phase 2: Core Development
Phase 3: Prototype & Features
Phase 4: QA & Deployment